IAIA’05 target dates (in-house use only)

For discussion/revision by program chairs as needed.

Bolded items are published.

Updated 1/27/05

# 31 December	• Early Bird registration ends

31 January		• Student fee waiver applications due

# 28 February	• Abstracts due.  Note:  the original published date was 31 January

14 March	• All abstracts reviewed by session chairs (abstracts should have been reviewed on a continuing  basis, so although many will come in on deadline, from 28 Feb to 14 March – 11 days -- should allow enough time.)

• Session chairs should have contacted all presenting authors regarding acceptance status and advising of registration deadline

# 1 March	• Regular registration rate ends*

22 March	• Deadline for presenting author’s registration.  Note: the original published date was 1 March

28 March	• Registrations processed

30 March	• Presentations without presenting author registered dropped from program (status indicated online); session chairs prepare or adjust detailed schedule

# 31 March	• Exhibitors deadline

• Tech visit deadline

• Delegate packet requests deadline

• Training course deadline

• Quickpass deadline

• Special A/V requests

• Student/mentor forms due

6 April	•  “Call” day (phone/e-mail reminders to session chairs about 7 April)

7 April	• Detailed schedule of sessions due from session chairs to Wes & Charlotte

22 April	• Detailed schedule of sessions due to HQ from Wes & Charlotte (from 7-22 April allows time for reviews, scheduling, working with session chairs, etc.)

Approx 22 April	• Session chairs need to send final acceptance notices to authors.

# 28 April	• Hotel cutoff

• Last-minute changes to text/info for final program. Note: this date should not be moved. The layout will need to be finalized and then it should have a minimum of 2 proofreadings; as-is, this is already a tight time frame to get it to the printer by 12 May.

12 May	• Final program to printer (allows the printer 10 days for prep, print, and delivery by 27 May; this is minimum amount of time needed)

28 May	• Conference begins